California Department of Social Services | CDSS

Child Welfare Digital Services | CWDS

# CWS-CARES Legislative Update

December 2024

# Executive Summary

Highlights

- Milestone 15: Hearing Framework completed its initial development in December.

- Milestone 10: Case Closure milestone returned to green status in December.

- Milestone 14: Warrants completed initial development in December.

Challenges

- Milestone 7.1:  Case Management Assessment (CMA) design is in red status for December due to clarifications from both the vendor and the Salesforce teams specifically around specifications for the data communication between CWS-CARES and the P-CIS tool.

- Milestone 26.1: Facility Management System (FMS) design is in red status for December due to a delay in CDSS contract execution for the FMS vendor onboarding, now pushed to mid-March 2025.

# Simplified Milestone Development Dashboard

The milestone chart below identifies the development progress for business requirements, design, build, vendor testing and state testing for each milestone grouped together by Extended User Scenario Testing (EUST).

EUST 2

| Milestone | Milestone Start Date | Milestone End Date | Business Requirement | Design | Build | Vendor Testing (SIT) | State Testing (QA) | % Ready for User Feedback |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Milestone 01: Service Provider Profile | 2022-05-02 | 2023-01-31 | 100% ✔ | 100% ✔ | 100% ✔ | 100% ✔ | 100% ✔ | 100% ✔ |
| Milestone 02: Services | 2022-05-02 | 2023-01-31 | 100% ✔ | 100% ✔ | 100% ✔ | 100% ✔ | 100% ✔ | 100% ✔ |
| Milestone 06: Case Management: Engagement | 2022-07-18 | 2023-12-01 | 100% ✔ | 100% ✔ | 100% ✔ | 100% ✔ | 100% ✔ | 100% ✔ |
| Milestone 08: Placement | 2022-10-10 | 2024-04-19 | 100% ✔ | 100% ✔ | 100% ✔ | 100% ✔ | 100% ✔ | 100% ✔ |
| Milestone 15: Court Hearing Framework | 2023-01-30 | 2025-02-28 | 100% ✔ | 100% ✔ | 100% ✔ | 100% ✔ | 100% ✔ | 100% ✔ |
| Milestone 15.1: JNET | 2023-05-30 | 2024-12-06 | 100% ✔ | 100% ✔ | 100% ✔ | 100% ✔ | 100% ✔ | 100% ✔ |
| Milestone 19: Request Determination | 2022-11-07 | 2025-02-27 | 100% ✔ | 100% ✔ | 100% ✔ | 100% ✔ | 100% ✔ | 100% ✔ |
| Milestone 20: Redetermine Eligibility & Placement/Information Change | 2023-06-19 | 2025-02-28 | 100% ✔ | 100% ✔ | 100% ✔ | 84% ✓ | 84% ✓ | 60% ✓ |

EUST 3

| Milestone | Milestone Start Date | Milestone End Date | Business Requirement | Design | Build | Vendor Testing (SIT) | State Testing (QA) | % Ready for User Feedback |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Milestone 6.1: Prevention Services | 2023-03-27 | 2025-12-30 | 100% ✔ | 100% ✔ | 100% ✔ | 100% ✔ | 100% ✔ | 100% ✔ |
| Milestone 07: Case Plan | 2023-09-11 | 2025-12-30 | 100% ✔ | 55% ✓ | 3% ✓ | 3% ✓ | 3% ✓ | 3% ✓ |
| Milestone 7.1: Case Management Assessment (CMA) | 2024-04-15 | 2025-12-26 | 100% ✔ | 3% ⚠ | 1% ✓ | 1% ✓ | 1% ✓ | 1% ⚠ |
| Milestone 09: Case Management: Engagement & Services | 2022-12-05 | 2025-12-30 | 100% ✔ | 100% ✔ | 100% ✔ | 100% ✔ | 100% ✔ | 100% ✔ |
| Milestone 10: Case Closure | 2023-02-27 | 2025-12-30 | 100% ✔ | 12% ✓ | 76% ✓ | 76% ✓ | 76% ✓ | 76% ✓ |
| Milestone 10.1: Structured Decision Making (SDM) | 2023-04-24 | 2025-07-11 | 100% ✔ | 93% ✓ | 71% ✓ | 59% ✓ | 43% ✓ | 23% ✓ |
| Milestone 11: Aftercare & Re-Entry | 2023-12-04 | 2025-12-30 | 100% ✔ | 12% ✓ | 0% ✓ | 0% ✓ | 0% ✓ | 0% ✓ |
| Milestone 13: Adoption | 2024-02-12 | 2025-12-30 | 100% ✔ | 12% ✓ | 0% ✓ | 0% ✓ | 0% ✓ | 0% ✓ |
| Milestone 14: Warrants | 2023-01-03 | 2024-12-30 | 100% ✔ | 100% ✔ | 100% ✔ | 100% ✔ | 100% ✔ | 100% ✔ |
| Milestone 16: Jurisdiction and Disposition | 2023-11-06 | 2025-12-30 | 100% ✔ | 48% ✓ | 1% ✓ | 1% ✓ | 1% ✓ | 1% ✓ |
| Milestone 17: Status Reviews | 2024-01-02 | 2025-12-30 | 100% ✔ | 48% ✓ | 0% ✓ | 0% ✓ | 0% ✓ | 0% ✓ |
| Milestone 18: Other Hearings | 2023-05-22 | 2025-12-30 | 100% ✔ | 48% ✓ | 39% ✓ | 38% ✓ | 38% ✓ | 38% ✓ |
| Milestone 20.1: Foster Care Eligibility Determination (FCED) | 2023-01-30 | 2025-12-26 | 100% ✔ | 91% ✓ | 79% ✓ | 78% ✓ | 68% ✓ | 59% ✓ |
| Milestone 21: Eligibility Programs | 2023-04-24 | 2025-12-30 | 100% ✔ | 97% ✓ | 97% ✓ | 97% ✓ | 97% ✓ | 97% ✓ |
| Milestone 23: Track Administrative Costs | 2024-03-25 | 2025-12-30 | 100% ✔ | 5% ✓ | 0% ✓ | 0% ✓ | 0% ✓ | 0% ✓ |
| Milestone 23.1: Service Delivery Tracking | 2024-03-25 | 2025-12-30 | 100% ✔ | 5% ✓ | 0% ✓ | 0% ✓ | 0% ✓ | 0% ✓ |
| Milestone 23.2: County Expense Claim Reporting Information System (CECRIS) | 2024-06-17 | 2025-10-31 | 100% ✔ | 0% ✓ | 0% ✓ | 0% ✓ | 0% ✓ | 0% ✓ |
| Milestone 24: Track Assistance Costs | 2024-01-01 | 2025-12-30 | 100% ✔ | 5% ✓ | 0% ✓ | 0% ✓ | 0% ✓ | 0% ✓ |
| Milestone 26: Maintain Resource Family Home | 2023-12-04 | 2025-12-30 | 100% ✔ | 44% ✓ | 0% ✓ | 0% ✓ | 0% ✓ | 0% ✓ |
| Milestone 26.1: Facility Management System (FMS) | 2024-03-25 | 2025-11-28 | 100% ✔ | 0% ⚠ | 0% ✓ | 0% ✓ | 0% ✓ | 0% ⚠ |
| Milestone 27: Complaints | 2023-06-19 | 2025-12-30 | 100% ✔ | 48% ✓ | 68% ✓ | 67% ✓ | 62% ✓ | 59% ✓ |
| Milestone 28: Legal Action | 2024-02-26 | 2025-12-30 | 100% ✔ | 44% ✓ | 0% ✓ | 0% ✓ | 0% ✓ | 0% ✓ |

EUST 2

Milestone 15 - Court Hearing Framework

#### Description:

Court Hearing Framework equips workers to prepare for petition hearings which include all activities related to any petition that is filed by Child Welfare. They will be able to capture all findings and orders from the Court and receive processes, and store information regarding the court results. This milestone enables workers to submit a calendar request to the Court. Workers can create, amend, and submit a petition for supervisor approval and then to submit a petition to Court. Rulings from Court hearings can be documented in CWS-CARES and the system will assist in the preparation of a Court report and record the results.

#### Current Status:

All product development work is now complete for this milestone. This milestone will be included in EUST 2 starting in late March 2025.

## Milestone 15.1 – JNET

#### Description:

This milestone is a legacy interface. The interface is being kept in place for CWS-CARES Version 1 (V1) at the request of San Bernardino County. The functionality in CWS-CARES V1 will be identical to the existing functionality in CWS/CMS. The interface will update the courts system with current assignments in CWS-CARES that applies to San Bernardino only.

#### Current Status:

All product development work is now complete for this milestone. This milestone will be included in EUST 2 starting in late March 2025.

## Milestone 20 - Redetermine Eligibility & Placement/Information Change

#### Description:

Redetermine Eligibility equips the CWS-CARES user and the Foster Care Eligibility Worker with the ability to collaborate and complete the eligibility re-determination process, using the Foster Care Eligibility Determination (FCED) interface between CWS-CARES and CalSAWS. The milestone allows the CWS-CARES user to notify the Foster Care Eligibility Worker via CalSAWS when a youth placed in residential facilities does not meet Qualified Residential Treatment Program (QRTP) requirements or when the requirements for child’s placement in a QRTP are not met.

#### Current Status:

Build is now complete while testing activities continue. Expected completion date for this milestone is February 2025 and will be included in EUST 2 planned for end of March 2025.

EUST 3

## Milestone 7 – Case Plan

#### Description:

Case Plan establishes the foundation and central unifying tool in child welfare services. The milestone equips the worker to partner with the child, family, and care team to develop, monitor, and provide services and case management to assure the child’s best interest is met through the provision of a safe environment. Concurrent planning is accommodated to bolster the expediency of a permanent arrangement for the child if the maintenance or reunification efforts with the family of origin fail. Automation of central safety and risk assessment findings (i.e., CANS and SDM) facilitates the monitoring of the case plan and its impact on the child’s safety. Other key plans include the Transitional Independent Living Plan (TILP), the 90-Day Transition Plan, the Plan of Safe Care, the Shared Responsibility Plan are also included.

This milestone seeks to unify all the plans into one Universal Case Plan, allowing the worker to provide more client-friendly, meaningful action items from one central document. To align with program readiness this milestone also covers Family First Prevention Services Act (FFPSA), including both the Community and Title IV-E Pathways, originally scheduled for Prevention Services.

#### Current Status:

Design activities continue to be in progress. Hands-on keyboard user feedback session is December 2025 with EUST 3 scheduled for February 2026.

## Milestone 7.1 – Case Management Assessment (CMA)

#### Description:

Case Management Assessment will provide information on completed Child and Adolescent Needs and Strengths (CANS) Assessments, National Youth in Transition Database (NYTD) Survey, Child, and Family Teams (CFT) Survey, Independent Living Plan (ILP), and Supervised Independent Living Placement (SILP) using the Person-Centered Intelligence System (P-CIS) with our partner Opeeka. This interface will be accessed using a Single Sign-On (SSO) method where the worker in CWS-CARES will not need to use different credentials to log in and will rather be directed from CWS-CARES into the P-CIS tool to complete the necessary assessment.

#### Current Status:

Progress health is red for the month of December owing to clarifications from the vendor and Salesforce teams specifically around specifications for the data communication between CWS-CARES and the P-CIS tool.

The clarifications are in progress, and the design completion is projected for February 2025. This milestone will be included in the EUST 3 scheduled for February 2026.

## Milestone 10 - Case Closure

#### Description:

Case Closure provides social workers with the ability to assess cases for closure, finalize and close a case, and support any other areas of practice related to the ending of a child welfare case. This ultimately equips the social worker with the best practices for family engagement in transition and aftercare planning, with the goal of helping families prepare for their exit from Child Welfare and reduce the likelihood they will need services in the future.

#### Current Status:

Design is nearing completion while build activities continue. Hands-on keyboard user feedback session is December 2025 with EUST 3 scheduled for February 2026.

Milestone 10.1 - Structured Decision Making (SDM)

#### Description:

This milestone is a suite of decision-support tools that promotes safety and well-being for children and adults. The SDM model combines research with best practices, offering workers a framework for consistent decision making and offering agencies a way to target in-demand resources toward those who can benefit most. The SDM Assessment Tools that will be in CWS-CARES are Hotline Assessment, Risk Assessment, Risk Re-Assessment, Substitute Care Safety Assessment, Congregate Care Safety Assessment, In-Home Safety Assessment, and Reunification Assessment.

#### Current Status:

Design is nearing completion while build activities continue. Expected completion date for this milestone is July 2025 and will be included in the EUST 3 scheduled for February 2026.

## Milestone 11 – Aftercare and Re-Entry

#### Description:

Aftercare & Re-Entry equips the worker with a platform for intentional planning for aftercare services as a family, child, or youth approaches case closure. The structured format for capturing this planning process (i.e., CFT, case plan, family preservation, etc.) assures that those exiting child welfare case management services are doing so with services, people, and resources in place to provide ongoing support. This is inclusive of informing the family, child, or youth about re-entry should their needs in the future warrant even more support.

#### Current Status:

Business requirements activities are complete while holistic design activities commence. Hands-on keyboard user feedback session is December 2025 with EUST 3 scheduled for February 2026.

## Milestone 13 – Adoptions

#### Description:

Adoption improves monitoring of the adoption processes and activities, including document preparation and tracking for adoption finalization. Increases compliance with State rule for Termination of Parental Rights (TPR) and other adoption-related requirements. Increases visibility in the adoption process, including adoption stability, re-entry following adoption, and post-adoption services support.

#### Current Status:

Business requirements activities are complete while holistic design activities continue. Hands-on keyboard user feedback session is December 2025 with EUST 3 scheduled for February 2026.

## Milestone 14 - Warrants

#### Description:

Warrants equips the worker to submit a request within a warrant application process with the assistance and accompaniment of law enforcement officials. This milestone enables workers to request a warrant be issued by a court for a child protective custody, entry into a home, interview a child, and conduct medical examinations. It also documents the ruling on a warrant.

#### Current Status:

Final state review is now complete. Hands-on keyboard user feedback session is December 2025 with EUST 3 scheduled for February 2026.

## Milestone 16 – Jurisdiction and Disposition

#### Description:

Jurisdiction and Disposition Hearings equips workers to complete the noticing process, prepare for disposition hearings for both detained and non-detained youth, and conduct the necessary preparations for jurisdiction hearings of all petition types. The noticing capabilities in this milestone will overlap with many of the hearing types from Warrants, Court Hearing Framework, and Other Hearings, and ensure proper documentation for hearings are received by the relevant parties. This milestone enables workers to identify parties to send a notice to, complete a diligent search to locate the absent parent, and notice appropriate parties. The milestone also equips workers to gather and document all evidence to support the Jurisdiction hearing petition allegations, and to obtain a social history from the parents for Disposition hearings.

#### Current Status:

Business requirements are complete while design activities continue. Hands-on keyboard user feedback session is December 2025 with EUST 3 scheduled for February 2026.

## Milestone 17 – Status Reviews

#### Description:

Status Reviews equips workers to prepare for a wide variety of status review hearings. This milestone supports the reporting and the documentation outputs from Family Reunification, Family Maintenance, Non-Minor Dependent, and Permanent Plan hearings. Workers will be able to capture all findings and orders from the Court, and store information regarding the court results. This milestone also enables workers to submit case plans for a variety of review hearings, evaluate case progress and conduct Safety Assessments, create and submit Permanency Plans, and create and file letters of Guardianship.

#### Current Status:

Business requirements are complete while design activities continue. Hands-on keyboard user feedback session is December 2025 with EUST 3 scheduled for February 2026.

## Milestone 18 - Other Hearings

#### Description:

Other Hearings extends the Court Hearing Framework to cover additional hearing types, including:

366.26 Selection and Implementation. This type of hearing is set after reunification services are terminated or not offered to parents. The purpose of this hearing is to determine and order the Permanent Plan for the child, which may include a plan of Adoption, plan of Tribal Customary Adoption, plan of Legal Guardianship or plan of Another Permanent Planned Living Arrangement (APPLA).

Special or Interim Review. Examples of special/interim hearing topics include Case Plan Compliance, Placement Update, Psychotropic Medication Review, and 15-Day Review Hearing. This milestone also covers hearings related to Nonminor Dependent Re-entry into Extended Foster Care, the 241.1 Joint Assessment with Juvenile Probation, and the Adoption Finalization Hearing. While it will equip social workers to create an Adoption Court Case separate from the Juvenile Court case, it does not cover the filing of Adoption or Adoption Assistance Program (AAP) forms.

Ex Parte Court Filings and Requests for Special Orders. Ad hoc filings may include requests for psychotropic medication, surgical procedures, other invasive medical treatment, use of general anesthesia, travel orders, paternity testing, psychological evaluation orders and requests for Interstate Compact on the Placement of Children placement. This milestone also includes processing records requests and requests for discovery in preparation for court.

#### Current Status:

Business requirements activities are complete while holistic design activities continue. Hands-on keyboard user feedback session is December 2025 with EUST 3 scheduled for February 2026.

## Milestone 20.1 – Foster Care Eligibility Determination (FCED)

#### Description:

The FCED interface enables collaboration between the CWS-CARES users and the Foster Care Eligibility Worker by exchanging relevant data about a child for an Eligibility Determination Benefits Calculation (EDBC), including the request status and eligibility results, between CWS-CARES and CalSAWS.

This interface between CWS-CARES and CalSAWS/FCED will remove the need for paper-based processes that rely on the physical exchange of forms between workers. Workers will no longer need to manually enter data from one system to another via those paper forms and automate the eligibility determination process in a cost effective and efficient manner. This will also improve data accuracy, improve ability to report statistics, reduce calls to Foster Care and CWS employees for information, and reduce staff and equipment costs.

.

#### Current Status:

Design activities are nearing completion while build continues. Expected completion date for this milestone is December 2025.

## Milestone 21 - Eligibility Programs

#### Description:

Eligibility Programs extend the Eligibility Framework established in Request Determination to include other foster care programs. These programs include Kin-GAP (Kinship Guardianship), NRLG (Non-Related Legal Guardian), AAP (Adoption Assistance Programs) and EFC (Extended Foster Care).

#### Current Status:

Design activities near completion while build continues to be in progress. Hands-on keyboard user feedback session is December 2025 with EUST 3 scheduled for February 2026.

## Milestone 23 – Track Administrative Costs

#### Description:

This milestone covers the process of creating a directory for child welfare-related program codes. This directory will enable the tracking of costs within the system and establish a foundation for financial management tracking in CWS-CARES. With this milestone, state fiscal users will have the ability to add and update Program Codes (PCs), Allocations, and Ledger pages through the County Expense Claim (CEC) interface in the County Expense Claim Reporting Information System (CECRIS). This functionality will allow fiscal workers to summarize all available funding sources, which can then be used to better support child welfare programs by leveraging existing funding streams.

#### Current Status:

Business requirements activities are complete while holistic design activities begin. Hands-on keyboard user feedback session is December 2025 with EUST 3 scheduled for February 2026.

## Milestone 23.1 – Service Delivery Tracking

#### Description:

This milestone enables county workers to draft correspondence to the service providers in CWS-CARES. Using the CWS-CARES portal, service providers can log in and conveniently update their provider profile and contract information. The milestone also serves as a platform for service providers to access individual information and family prevention services plan directly and efficiently. Additionally, service providers can utilize the portal to submit cost-tracking information for the services they have provided. The milestone allows various state and county users to generate reports that aggregate service costs by program code, services, and provider. This data will help counties track and analyze spending patterns, identify areas for improvement, and make informed decisions regarding resource allocation.

#### Current Status:

Business requirements activities are complete while holistic design activities begin. Hands-on keyboard user feedback session is December 2025 with EUST 3 scheduled for February 2026.

## Milestone 23.2 – County Expense Claim Reporting Information System (CECRIS)

#### Description:

This milestone will allow users to view county-specific administrative claim information from the County Expense Claim (CEC) in CECRIS in a centralized area for financial management in CWS-CARES. This information will be fed from a unidirectional data exchange with CECRIS. This information will be read-only to all CWS-CARES users. State fiscal users will have the ability to generate report(s) by program code in CWS-CARES to support accurate reporting on state and federal reports, including the Title IV-E Programs Quarterly Financial Report (CB-496).

#### Current Status:

Business requirement activities are now complete. Expected completion date for this milestone is October 2025 and will be included in the EUST 3 scheduled for February 2026.

## Milestone 24 – Track Assistance Costs

#### Description:

Assistance Costs covers the process of gathering child-specific assistance cost information from the California Statewide Automated Welfare System (CalSAWS) including information on aid codes, supplemental rates, dates of payment, level of care, educational travel, and any specialized care increments. The purpose of gathering this child-specific assistance cost information is to aggregate the data in a format that can be used to validate the CA-800 assistance claims. This milestone aims to facilitate the process of tracking and reporting child-specific costs that are required for state and federal reporting (such as CB 496 report). By efficiently aggregating and organizing this information, it enables users to generate accurate and comprehensive reports that meet the reporting standards mandated by CWS-CARES.

#### Current Status:

Business requirements are complete while design activities begin. Hands-on keyboard user feedback session is December 2025 with EUST 3 scheduled for February 2026.

## Milestone 26 – Maintain Resource Family Home

#### Description:

This milestone covers the maintenance and support of the Resource Family Home. This milestone equips Resource Family Approval (RFA) workers to monitor Resource Family Homes while increasing engagement with families to help and retain qualified Resource Families. In instances where the Resource Family Home is not meeting the standards, the RFA Worker will be able to document what needs to be corrected or follow the process to close the home. The milestone equips the RFA Worker with the tools to maintain the home by contact logs, child welfare history, training updates, and utilizing automated form generation with e-signatures.

#### Current Status:

Business requirements are complete while design activities continue. Hands-on keyboard user feedback session is December 2025 with EUST 3 scheduled for February 2026.

## Milestone 26.1 – Facility Management System (FMS)

#### Description:

The delivery of this interface will populate placement providers from the Licensing Information System-Facility Automation System (LIS-FAS) into the CWS-CARES provider directory. An accurate provider profile with confirmed licensure information from Community Care Licensing in the CWS-CARES provider directory will allow caseworkers to make better placement decisions. The provider directory will also organize data and track placements and the associated costs of those placements, as well as tie outcomes to the provider. For CWS-CARES V1, the FMS interface will be unidirectional and will not write back or send data back to FMS. The scope of the FMS Interface for CWS-CARES V1 is limited to LIS and FAS data only.

#### Current Status:

Although business requirements are complete, there is a delay with the start of holistic design activities due to a delay in CDSS contract execution for the FMS vendor onboarding, which has been pushed to mid-March 2025. This milestone will be included in the EUST 3 scheduled for February 2026.

## Milestone 27 - Complaints

#### Description:

Complaints covers the process of screening a complaint and investigating a complaint against a Resource Family Home. The milestone equips the RFA Worker with the ability review the complaint, add allegations as necessary, and access RFH home information in CWS-CARES. This allows the RFA Worker to make an informed decision on the best pathway for a complaint. In instances when a complaint warrants an investigation, the milestone equips the RFA Investigator with the tools to complete a thorough and timely investigation by utilizing contact logs, complaint history, allegation updates, and automated form generation with e-signature capabilities.

#### Current Status:

Business requirements activities are complete while holistic design activities continue. Hands-on keyboard user feedback session is December 2025 with EUST 3 scheduled for February 2026.

## Milestone 28 – Legal Action

#### Description:

Legal Action covers the legal consultation to Resource Family Homes and handles the outcomes in a confidential manner. The RFA Worker will be equipped to schedule legal consult when there are administrative action requests. The RFA Worker will aid in the process of Legal Action with the Resource Family Home by providing resources and monitor the legal consults. The milestone equips the RFA Worker with the tools to provide timely legal consultation through contact logs, permission sets, child welfare history, and utilizing automated form generation with e-signatures.

#### Current Status:

Business requirements are now complete while design activities continue. Hands-on keyboard user feedback session is December 2025 with EUST 3 scheduled for February 2026.

# User Feedback

The schedule for user feedback has been finalized and all future EUST sessions have added to the project master schedule. The primary focus during this reporting period was addressing user stories created following EUST 1, as well as internal walkthroughs by the project teams in preparation for EUST 2. Below is a list of all milestones, their respective scheduled EUST session and the duration of each phase.

| EUST | Milestones |  | Duration |
| --- | --- | --- | --- |
| EUST 2 | 01 – Provider Profile 02 – Services 06 – Case Management: Engagement 08 – Placement 15 – Court Hearing Framework 15.1 – Interface – JNET 19 – Request Determination 20 – Redetermine Eligibility & Placement/Information Change 20.1 – Interface – FCED (partial) |  | 4 weeks Mar – Apr 2025 |
| EUST 3 | 06.1 – Prevention Services 07 – Case Plan 07.1 – Interface – CMA 09 – Case Management: Engagement & Services 10 – Case Closure 10.1 – Interface - SDM 11 – Aftercare & Re-entry 13 – Adoption 14 – Warrants 16 – Jurisdiction and Disposition Hearing 17 – Status Reviews | 18 – Other Hearings 20.1 – Interface – FCED (remainder) 21 – Eligibility Programs 23 – Track Administrative Costs 23.1 – Service Delivery Tracking 23.2 – Interface – CECRIS 24 – Track Assistance Costs 26 – Maintain Resource Family Home 26.1 – Interface – FMS (LIS/FAS data) 27 – Complaints 28 – Legal Action | 6 weeks Feb – Mar 2026 |
| EUST 3 – Reports/Admin | 29 – Federal Reports 30 – State Reports 31 – Ad hoc Reports 32 – Admin Services Console |  | 6 weeks Mar – Apr 2026 |
| EUST 4 | End-to-End Validation of all Product and Interface Milestones |  | 4 weeks May – Jun 2026 |

The following graphs reflect the same breakdown of EUST 1 user feedback stories as reported in prior months while factoring in data from two preceding months.

Acronyms: Business Requirements Closed (BRC); Submitted to BRC (SBRC); Product Delivery Lead (PDL); System Integration Testing (SIT); Quality Assurance (QA)

Acronyms: Business Requirements Closed (BRC); Submitted to BRC (SBRC); Product Delivery Lead (PDL); System Integration Testing (SIT); Quality Assurance (QA)

# Data Conversion

The data conversion team continued to focus on the activities related to the active milestones listed above. The team extracted additional documents, bringing the total to 7,940,694 as of December 2024.  Cycle 4 practices validation concluded in December. During practices validation all county and tribe organizations are invited to review data conversion source to target mappings (STTM) and account for any business requirements specific to counties and CDSS validation according to Federal and State reporting requirements. Cycle 4 data conversion data validation will begin in January 2025. In data validation, core constituent counties log into the CWS-CARES application to compare data against CWS/CMS and validate data is converted as appropriate.

| Extract | As of | Total # of Doc | Planned | Extracted | Infected | Deleted by Worker or Corrupted |
| --- | --- | --- | --- | --- | --- | --- |
| Phase 1 | Day 69 of 69 (6/15) | 68,827,906 (As of 2/1/2023) | 68,827,906 (By Day 69) | 68,793,343 | 2,455 | 34,563 |
| Phase 2 | Day 6 of 6 (6/27) | 3,342,252 (As of 6/16/2023) | 3,342,252 (By Day 6) | 3,330,762 | 0 | 11,490 |
| Phase 3 | Ongoing (12/26) | Continuous until Go-Live | 7,994,730 | 7,940,694 | 0 | 54,036 |

# User Adoption Summary

Pilot Status Update – During the month of December, the implementation team held three of eight County Participant Pilot Workgroup meetings with six counties identified as contributors to CWS-CARES pilot considerations. The final session will be held on January 7 to discuss the project’s Pilot recommendation. The recommendation will be submitted to the CWDS Board of Directors for discussion during the January 23 board meeting.

County Child Welfare Engagement – The implementation team continues to conduct individual monthly meetings with each county to discuss upcoming Go-Live readiness activities. With the completion of quarter 4 implementation readiness activities, the team is preparing to deliver Go-Live Readiness Dashboards to each county during the month of January.

EUST – The implementation and training teams continue to prepare for EUST by developing training materials for the associated milestones in EUST 2.

CDSS Executive Briefings – In collaboration with the CDSS Implementation Coordinator, the team finalized the CWS-CARES V1 Go-Live Readiness Checklist Framework for CDSS. The framework will utilize the baseline readiness checklist for counties with proposed revisions that support the uniqueness of the different CDSS Divisions. Specific readiness tasks for implementation management, Organizational Change Management (OCM), and training are dependent on the division’s combination of system-use types. The implementation team conducted Implementation Kickoff meetings with CDSS Finance & Accounting Division to initiate formal continued implementation readiness support. Additionally, the implementation team continues to meet with CDSS divisions regarding training logistics. The purpose of the training logistics meetings is to discuss how CDSS instructor-led training will be delivered, including any unique needs.

Probation Engagement – The implementation team continued to complete preparation activities for Probation Executive Briefings and kick-off meetings, beginning in mid-February 2025. The Executive Briefings and kick-off meetings will discuss county probation chief’s role as sponsors, the implementation approach for engagement, and recommendations for how county probation organizations may consider structing their Implementation teams to complete readiness activities in preparation for the CWS-CARES Go-Live.

Engagement with Tribes with Title IV-E Agreements with CDSS – The implementation team completed informal sessions with CDSS and the Office of Tribal Affairs to better understand the needs of the Karuk and Yurok Tribes prior to engaging directly with the Tribes. The team has scheduled CWS-CARES implementation kick-off meetings with the Yurok and Karuk Tribes to occur on February 19 and 26, 2025.

ACF Monthly Reporting on User Engagement & Adoption – The Strategic Communications Team submitted the thirteenth (13) Administration for Children and Families (ACF) monthly report on user engagement and adoption for the December meeting. This month’s ACF report included results from the third Core Constituent Survey. The Core Constituent surveys capture participant sentiment, identify existing gaps and areas for improvement and enable the Product Team to develop targeted strategies to improve the process. The first survey was sent in May 2024, the second survey was sent in August 2024, and this survey was sent in November 2024. The CWS-CARES Project invited 90 Core Constituents from 8 service areas, 37 counties, and 1 tribe to participate, and received 60 total responses. Outcomes and observations from the Core Constituent surveys are added to a shared action item tracker and addressed by project staff. Outcomes include: the need for inclusive training resources and onboarding processes; more guidance for Core Constituents to identify who should attend specific meetings; more time requested from participants for demonstrations and feedback; a conflict with participant availability for meetings; lack of a clear agenda for meetings; regular, detailed demonstrations with CWS/CMS comparisons are needed to support informed decisions and meaningful feedback; and, data conversion processes are unclear, hindering participants from providing meaningful input. An action plan was identified to address each of these outcomes.

External Communications – The Strategic Communications Team also published the fourth issue of the CARES Explorer, a full-length newsletter published quarterly to keep external audiences informed on specific CWS-CARES topics and information items. The team also published the monthly CWS-CARES Meeting Calendar to the CWDS website. This calendar captures recurring meetings hosted and facilitated by CWS-CARES Project staff and include the CARES Implementation Meeting, CARES workgroup meetings, and Core Constituent demonstrations and service area meetings. The team also updated the CARES Experiences Timeline, which includes county and organization activities and tasks that provide experiences for direct observation or participation in CWS-CARES up to Version 1 Go-Live. The Strategic Communications Team also launched the registration link for the January 29th CWS-CARES Stakeholder briefing, with 173 registrants to date. The CWS-CARES project facilitates period webinars for stakeholders to promote user engagement, highlight system functionality and provide real-time project updates. The team also moved the CWS-CARES Library into production. The CWS-CARES Library will be a centralized, searchable repository of foundational CWS-CARES project information on the CWDS website.

Completed Communications Work Products – The Strategic Communications Team also finalized the following work products: EUST 2 user outreach communications, an infographic of External Systems phases and timelines, draft talking points and presentation for the January 22nd CWDS All-Staff meeting, refine the Strategic Communications Roadmap to include 2025 activities, and execute on the SafeMeasures® communication plan.

Budget and Expenditures

2023-24 CWS-CARES Report Summary

| OTSI Spending Authority Budget Item | 2023/24 Budget¹ | 2023/24 Expenditures2 |
| --- | --- | --- |
| Personal Services | $12,737,690 | $10,907,261 |
| Other Operating Expenses & Equipment (OE&E) | $17,175,146 | $11,940,969 |
| Data Center Services | $3,287,333 | $2,355,399 |
| Contract Services | $120,997,254 | $94,204,796 |
| Enterprise Services | $6,054,638 | $5,324,199 |
| OTSI Spending Authority Total | $160,252,061 | $124,732,624 |

| CDSS Local Assistance Budget Item | 2023/24 Budget | 2023/24 Expenditures |
| --- | --- | --- |
| CDSS Salary & Benefits3 | $1,360,000 | $1,188,959 |
| CDSS OE&E (Includes Travel and Training)3 | $405,250 | $510 |
| Contract Services3,5 | $981,000 | $983,698 |
| County Regional Training Academy3 | $306,251 | $0 |
| Core Constituent Participation Costs4 | $23,000,000 | $5,211,227 |
| CDSS Local Assistance Total | $26,052,501 | $7,384,394 |

| Project Totals | 2023/24 Budget | 2023/24 Expenditures |
| --- | --- | --- |
| CWS-CARES Project Total | $186,304,562 | $132,117,018 |

1 2023/24 budget aligns with the SPR 6, with employee compensation adjustments, and is inclusive of CWS-CARES only costs. CARES-Live costs are not included.

2 Actual expenditures through June 2024 FI$Cal reports and approved invoices through December 31, 2024.

3 CDSS Local Assistance expenditures through June 2024. CDSS Salary & Benefits and OE&E expenditures through June 2024.

4 CDSS Fiscal Monitoring Unit confirmed four quarters of expenditures for Core Constituent Participation, and four quarters of expenditures for Tribal Core Constituents.

5 CDSS Local Assistance Contract Services is over budget due to an increase in IPOC cost rates.

Budget and Expenditures

2024-25 CWS-CARES Report Summary

| OTSI Spending Authority Budget Item | 2024/25 Budget¹ | 2024/25 Expenditures |
| --- | --- | --- |
| Personal Services2 | $14,332,163 | $3,865,674 |
| Other Operating Expenses & Equipment (OE&E)2 | $19,223,537 | $3,733,463 |
| Data Center Services2 | $3,349,028 | $591,790 |
| Contract Services2 | $133,673,182 | $26,700,510 |
| Enterprise Services2 | $6,117,578 | $1,514,231 |
| OTSI Spending Authority Total | $176,695,488 | $36,405,668 |

| CDSS Local Assistance Budget Item | 2024/25 Budget | 2024/25 Expenditures |
| --- | --- | --- |
| CDSS Salary & Benefits3 | $1,520,000 | $534,789 |
| CDSS OE&E (Includes Travel and Training)3 | $462,000 | $247 |
| Contract Services3 | $981,000 | $379,875 |
| County Regional Training Academy3 | $306,251 | $0 |
| Core Constituent Participation Costs4 | $30,822,770 | $1,528,812 |
| CDSS Local Assistance Total | $34,092,021 | $2,443,723 |

| Project Totals | 2024/25 Budget | 2024/25 Expenditures |
| --- | --- | --- |
| CWS-CARES Project Total | $210,787,509 | $38,849,391 |

1 2024/25 budget aligns with SPR 6 and is inclusive of CWS-CARES only costs. CARES-Live costs are not included.

2 Actual expenditures through October 2024 FI$Cal reports and approved invoices through December 31, 2024.

3 CDSS Local Assistance expenditures through November 2024. CDSS Salary & Benefits and OE&E expenditures through November 2024.

4 CDSS Fiscal Monitoring Unit confirmed one quarter of expenditures for Core Constituent Participation.

# Earned Value Management

CWS-CARES will be using Earned Value Management (EVM), in compliance with SPR 6, to measure project progress and forecast project completion in terms of budget and schedule. Each month, a Schedule Performance Index (SPI) and a Cost Performance Index (CPI) will be calculated using data sets provided by the project. An SPI of 1.0 indicates that the project is on schedule per the plan, an SPI below 1.0 indicates that the project is behind schedule, and an SPI above 1.0 indicates that the project is ahead of schedule. Similarly, a CPI of 1.0 indicates that the project is on budget related to the work performed. A CPI below 1.0 indicates that the project is over budget, and a CPI above 1.0 indicates that the project is under budget.

The data in the EVM dashboard below has been provided by the project as of December 15, 2024.

| Metric | 12/15/2024 | 11/15/2024 | 10/15/2024 | Description |
| --- | --- | --- | --- | --- |
| Planned V1 Percent Complete | 48% | 45% | 43% | Planned percent complete as of this date. |
| Actual V1 Percent Complete | 48% | 45% | 43% | Actual percent complete as of this date. |
| Schedule Performance Index (SPI) | 0.994 | 0.997 | 0.992 | Schedule performance of 1.0 or greater is on track, less than 1.0 is off track. |
| Cost Performance Index (CPI) | 1.210 | 1.299 | 1.274 | Cost performance of 1.0 or greater is on track, less than 1.0 is off track. |
| Estimated to Complete (ETC, V1) | $404,413,615 | $393,236,799 | $420,395,610 | Estimated cost to complete the project. |
| Estimated at Completion (EAC, V1) | $771,067,758 | $718,397,180 | $732,430,059 | Estimated cost at completion of the project. |
| Forecast V1 Completion | 11/10/2026 | 11/5/2026 | 11/12/2026 | Date V1 is forecasted to complete. |
| Forecast V2 Completion | 5/13/2028 | 5/7/2028 | 5/16/2028 | Date V2 is forecasted to complete. |
| Earned Cost (EC) | $443,720,273 | $422,355,566 | $397,540,703 | Budget for work actual completed to date. |
| Actual Cost (AC) | $366,654,143 | $325,160,381 | $312,034,449 | Actual cost for work completed to date. |

Legend

# Vendor Contracts

The following contracts or contract amendments were executed during the month of December 2024.

| Contract | Purpose | Contract Cost | Term | Notes |
| --- | --- | --- | --- | --- |
| County of Sacramento | County Subject Matter Expert Services | $626,081.67 | 1/1/25 - 4/30/28 | New agreement executed on 12/5/24. |
| Kern County | County Subject Matter Expert Services | $656,120.66 | 11/1/24 - 4/30/28 | New agreement executed on 12/18/24. |

The following contracts or contract amendments were submitted to the ACF during the month of December 2024.

| Contract | Purpose | Contract Cost | Term | Notes |
| --- | --- | --- | --- | --- |
| Taborda Solutions | Salesforce Services | $29,767,589.76 | 4/28/23 – 8/6/25 | ACF approval requested. This is an amendment to update Salesforce product offerings needed by the project. |
| xTerraLink, Inc. | V1 EUST 2 Security Testing Services | $250,000.00 | 1/6/25 - 5/5/25 | ACF Approval requested. New agreement for V1 EUST 2 Security Testing Services. |
| County of Sacramento | County Subject Matter Expert Services | $626,081.67 | 1/1/25 - 4/30/28 | Courtesy copy to ACF. New agreement executed on 12/5/24. |
| KPMG LLP | Financial Management Services | $3,500,000.00 | 8/1/22 to 11/30/25 | Courtesy copy to ACF. Amendment to exercise the last option of the agreement was executed on 10/31/24. |

High Priority Risks

For the December 2024 reporting period, zero (0) high priority risks were opened, closed, or continuing. The PMO continues to actively mitigate and resolve the project’s remaining medium and low priority risks in the bi-weekly risks and issues forum.

New High Priority Risks

There are zero (0) new high priority risks for the month of December.

Continuing High Priority Risks

There are zero (0) continuing high priority risks for the month of December.

Closed High Priority Risks

There are zero (0) closed high priority risks for the month of December.

High Priority Issues

For the December 2024 reporting period, zero (0) high priority issues were opened, closed, or continuing. The PMO continues to actively mitigate and resolve the project’s medium and low issues in the bi-weekly risks and issues forum.

New High Priority Issues

There are zero (0) new high priority issues for the month of December.

Continuing High Priority Issues

There are zero (0) continuing high priority issues for the month of December.

Closed High Priority Issues

There are zero (0) closed high priority issues for the month of December.

The infected files column identifies the number of documents that the conversion process identified as having a virus. These were not converted into CWS-CARES. The project has identified the associated counties and is working on a communication.

The deleted by worker/corrupted files column identifies the number of documents that the worker a) deleted from CWS/CMS during the conversion phases or b) tried to upload to CWS/CMS, but there was an issue, and the CWS/CMS mainframe was unable to save the file in its entirety.